## Summary
Work amount follow up
Group
| Project | Plan B
Phase | Hours planned | Hours realized
Specification | 52 | 0.85
System design | 44 | 0
Implementation | 66 | 0
Testin | 38 | 0
Management | 50 | 11.4
TOTAL | 250 | 12.25
(those phases are just for example)
Personal work amounts

## Antti
Work amount follow up
[5 empty] | Name | Antti
Group
[5 empty] | Project | Plan B
Hours realized
Date | Management | Spec | Design | Impl | Test | Descrtiption
2008-10-03 | 1 |  |  |  |  | Project meeting, preparation, task allocations
2008-10-07 | 0.25 |  |  |  |  | Project meeting, task allocations
2008-10-08 | 0.75 |  |  |  |  | Project plan body, chapter 7.1, finalizint the risk analysis
etc.
etc.
Yhteensä | 2 | 0 | 0 | 0 | 0 | 2

## Heidi
Work amount follow up
[5 empty] | Name | Heidi
Group
[5 empty] | Project | Plan B
Hours realized
Date | Management | Spec | Design | Impl | Test | Descrtiption
2008-10-08 | 1.5 |  |  |  |  | Esitteen suunnittelu ja toteutus
2008-10-09 | 0.5 |  |  |  |  | Kick-off
…
Yhteensä | 2 | 0 | 0 | 0 | 0 | 2

## Juha
Work amount follow up
[5 empty] | Name | Juha
Group
[5 empty] | Project | Plan B
Hours realized
Date | Management | Spec | Design | Impl | Test | Descrtiption
2008-10-03 | 0.5 |  |  |  |  | Projektipalaveri
2008-10-07 | 1.25 |  |  |  |  | Riskianalyysin suunnittelu, projektipalaveri
2008-10-10 | 0.5 |  |  |  |  | Projektipalaveri
2008-10-29 |  | 0.5 |  |  |  | Pelin tavoitteiden ideointia
2008-10-30 | 0.5 |  |  |  |  | Projektipalaveri
2008-11-05 | 0.15 | 0.1 |  |  |  | Keskustelu tehtäviin liittyen, pelikenttien ideointi
2008-11-06 | 0.5 | 0.25 |  |  |  | Projektipalaveri, musiikkiteeman ideointi
…
Yhteensä | 3.4 | 0.85 | 0 | 0 | 0 | 4.25

## Santtu
Work amount follow up
[5 empty] | Name | Santtu
Group
[5 empty] | Project | Plan B
Hours realized
Date | Management | Spec | Design | Impl | Test | Descrtiption
2008-10-03 | 0.5 |  |  |  |  | Project meeting
2008-10-08 | 1 |  |  |  |  | Project planning
Yhteensä | 1.5 | 0 | 0 | 0 | 0 | 1.5

## Virpi
Work amount follow up
[5 empty] | Name | Virpi
Group
[5 empty] | Project | Plan B
Hours realized
Date | Management | Spec | Design | Impl | Test | Descrtiption
2008-10-03 | 0.5 |  |  |  |  | Project meeting
2008-10-08 | 1
2008-10-09 | 0.5 |  |  |  |  | Kick-off
2008-10-10 | 0.5 |  |  |  |  | Project meeting
…
Yhteensä | 2.5 | 0 | 0 | 0 | 0 | 2.5

## Hidden
| Management | Specification | System designt | Implementation | Testing
Antti | 2 | 0 | 0 | 0 | 0
Heidi | 2 | 0 | 0 | 0 | 0
Juha | 3.4 | 0.85 | 0 | 0 | 0
Santtu | 1.5 | 0 | 0 | 0 | 0
Virpi | 2.5 | 0 | 0 | 0 | 0