## Summary
Work amount follow up
| Group | 1
| Project | Polestar
Phase | Hours planned | Hours realized
Specification | 6 | 3
System design | 12 | 5.25
Implementation | 46 | 46.75
Testin | 46 | 0
Management | 30 | 24
TOTAL | 140 | 79
(those phases are just for example)
Personal work amounts

## Andrew
Work amount follow up
[5 empty] | Name | Andrew
Group
[5 empty] | Project | Polestar
Hours realized
Date | Management | Spec | Design | Impl | Test | Descrtiption
2016-03-01 | 4 | 1 |  |  |  | Write project plan
2016-03-15 | 1 |  |  | 2 |  | Change project plan
2016-03-16 | 1.5 |  |  | 1.5 |  | meeting memo, schedule on track? work amount followup.
2016-03-22 | 0.25 |  | 0.25 | 3 |  | Visio, Polestar system concept diagram
2016-04-06 | 0.25 |  |  | 1 |  | SRSv1.doc first steps. Team emails.
2016-04-07 | 2 |  |  | 1.5 |  | SRSv1 sys diagram layout, UML, memo, follow up.
2016-04-13 | 1.5 |  |  | 2 |  | SRS system diagram , html, javescript, php interaction.
2016-04-19 | 1 |  |  | 2.5 |  | Website system diagram, meeting memo.
Yhteensä | 11.5 | 1 | 0.25 | 13.5 | 0 | 26.25

## Tu
Work amount follow up
[5 empty] | Name | Tu
Group
[5 empty] | Project | Polestar
Hours realized
Date | Management | Spec | Design | Impl | Test | Descrtiption
2016-03-01 | 4 | 1 |  |  |  | Write project plan
2016-03-15 | 1 |  | 2 |  |  | web page layout design
2016-03-16 |  |  | 3 |  |  | javascript. link left div floor level to right div floor map.
2016-03-22 | 0.25 |  |  | 3 |  | javascript, groundfloor plan per campus building.
2016-04-06 | 0.25 |  |  | 0 | 0 | Embassy visit. Visa beaurocrasy. Emailed absence.
2016-04-07 | 0.5 |  |  | 3 |  | Fixed javascript floorplan imagemapstar, described system func.
2016-04-13 | 0.25 |  |  | 3.25 |  | Javascript floor selection. Floor maps co-ords, "polishing"
2016-04-19 |  |  |  | 3.5 |  | 3 Table datbase design, js code
Yhteensä | 6.25 | 1 | 5 | 12.75 | 0 | 25

## Artem
Work amount follow up
[5 empty] | Name | Artem
Group
[5 empty] | Project | Polestar
Hours realized
Date | Management | Spec | Design | Impl | Test | Descrtiption
2016-03-01 | 4 | 1 |  |  |  | write project plan
2016-03-15 | 1 |  |  | 1.5 |  | web page floor maps polished in photoshop
2016-03-16 |  |  |  | 3 |  | web page floor maps polished in photoshop
2016-03-22 | 0.25 |  |  | 3 |  | web page floor maps polished in photoshop
2016-04-06 | 0.25 |  |  | 3.25 |  | web page floor maps polished in photoshop
2016-04-07 | 0.5 |  |  | 3 |  | web page floor maps polished in photoshop
2016-04-13 | 0.25 |  |  | 3.25 |  | Floor maps co-ords, "polishing" in photoshop.
2016-04-19 |  |  |  | 3.5 |  | Floor maps E building polishing in Photoshop
Yhteensä | 6.25 | 1 | 0 | 20.5 | 0 | 27.75

## Hidden
| Management | Specification | System designt | Implementation | Testing
Andrew | 11.5 | 1 | 0.25 | 13.5 | 0
Tu | 6.25 | 1 | 5 | 12.75 | 0
Artem | 6.25 | 1 | 0 | 20.5 | 0